## Slide 1: HPV Vaccination Workgroup
Heather Brandt, Sue Curry, Robin Vanderpool
University of South Carolina
University of Iowa
University of Kentucky
CPCRN Annual Grantee Meeting ~ May 24, 2016
This presentation was supported by Cooperative Agreement Numbers U48 DP005006, U48 DP005021, U48DP005014-01S2, U48 DP005000-01S2, and U48 DP005013 from the Centers for Disease Control and Prevention. The findings and conclusions in this presentation are those of the author(s) and do not necessarily represent the official position of the Centers for Disease Control and Prevention.

## Slide 2: Actively Involved CPCRN Centers
University of Washington
Oregon Health & Sciences University
University of Iowa
University of Kentucky
University of South Carolina
Coordinating Center
University of North Carolina
at Chapel Hill
Co-Leads
Heather Brandt, University of South Carolina
Sue Curry, University of Iowa
Robin Vanderpool, University of Kentucky
With support from CDC and NCI staff

## Slide 3: Workgroup Projects
HPV Vaccination Workgroup
Community-Clinical Linkages (All sites)
ACS Roundtable Pharmacy Grant (IA, KY, OR)

## Slide 4: Project Objectives and Aims
Overall Aim: To contribute to the science and evidence-base supporting innovative community-clinical linkages (CCLs) to increase HPV vaccination initiation and completion among adolescents and young adults.
Aim 1: Identify existing and potential CCLs applicable to HPV vaccination in our respective catchment areas and populations and assess their core components, processes, relationships, outcomes and/or areas for improvement for comparison across CPCRN sites using case study methodology.

## Slide 5: Project Objectives and Aims
Aim 2: Based on findings from Aim 1 and other ongoing research, identify opportunities to disseminate effective CCLs and/or build new linkages based on current activities/identified gaps and evaluate in a cross-site dissemination study aimed at increasing HPV vaccine initiation and completion across CPCRN sites.
Aim 3: Based on findings from Aim 2, disseminate – via multiple networks and platforms – a model(s) of successful CCL strategies used by community and clinical partners to increase HPV vaccine initiation and completion.

## Slide 6: CCL Work Plan Activities and Status
Aims and Related Activities | Status
Aim 1: Identification of existing and potential CCLs | 
Activity 1: Develop list of potential CCLs to be explored at each CPCRN site. | Completed
Activity 2: Draft CCL case study protocol methods document and solicit workgroup feedback. | Completed
Activity 3: IRB submission and approval. | Completed
Activity 4: Administration of CCL case study assessment | In progress
Activity 5: Conduct analysis of case study findings; draft and submit manuscript. Submitted abstract to the ACS Roundtable National Conference on Increasing HPV Vaccination (August 2016) | Jun-Aug 2016
Aim 2: Identify opportunities to disseminate and/or build CCLs | 
Activity 6: Each CPCRN site and their partner(s) will adapt and implement at least one CCL | Fall 2016 – Winter 2017
Activity 7: Evaluate CCLs at all CPCRN sites | Spring – Summer 2017

## Slide 7: Supporting Workgroup Activities
Workgroup members regularly contribute to the ACS National HPV Vaccination Roundtable Task Groups.
  School-Based Education (Vanderpool)
  Pharmacy-Located Vaccination (Kobrin)
  Healthcare Provider Training (Brandt)
Workgroup members have served as facilitators / subject matter experts / key note speakers in several HPV vaccination-related meetings, including:
  National Partners’ HPV Vaccine Workshop
  ACS National HPV Vaccination Roundtable Conference
  NCI HPV Vaccination Supplement Meetings
  Iowa HPV & Cancer Conference

## Slide 8: ACS HPV Roundtable Pharmacy Grant Activities and Status
Activities | Status
Submitted an application for funding to the ACS National HPV Vaccination Roundtable in November 2016 (Iowa, Kentucky, Oregon) | Completed
Submitted an abstract to the ACS Roundtable National Conference on Increasing HPV Vaccination (August 2016) | Completed
Continue work on the ACS Pharmacy-located HPV vaccination pilot project (Iowa, Kentucky, Oregon) through September 2016 | In progress

## Slide 9: Contribution / Impact in D&I Science
This project may accelerate the dissemination and implementation of evidence-based cancer prevention and control through the systematic identification and dissemination of best CCL practices.
Understand the role of CCLs in dissemination and implementation of evidence-based approaches to increase HPV vaccination, e.g.,
  Identify role of and best practices for CCLs
  Generalizability, scalability, sustainability, cost, outcomes
  Understand the mechanisms through which CCLs operate to disseminate evidence-based practices
Build on this understanding to support use of CCLs in D&I of evidence-based approaches to increase HPV vaccination
Notes: "Although CCLs are extremely valuable, questions related to generalizability, scalability, and sustainability of community-clinical linkages often go unanswered, and ongoing evaluation to identify effective models of community-clinical linkages, the circumstances in which they work (or alternatively, do not work), their cost, and their measured outcomes is needed."

## Slide 10: Dissemination Activities
Findings and best CCL practices will be shared via:
  Presentations
    Workgroup submitted an abstract to the ACS Roundtable National Conference on Increasing HPV Vaccination (August 2016)
    Plans to submit an abstract to the NCI Cancer Centers HPV Vaccination Meeting (June 2016)
  Manuscripts
  Reports (to be shared with CCLs and stakeholders)
  Social media
  Provider/public health organizations and community groups
  On-line repository of HPV vaccination CCL strategies

## Slide 11: Contribution / Impact in Cancer Prevention and Control
Through the systematic identification and dissemination of best CCL practices, HPV vaccination rates among different populations in varying community settings may be increased, ultimately impacting HPV-related cancer burden.
Establish/strengthen partnerships at participating CPCRN sites with local efforts in HPV vaccination.
Identify best practices common to varying locations and populations.
Findings will inform the development of recommendations with broad applicability.

## Slide 12: Issues and Questions for Discussion
Issues Encountered / Lessons Learned
Coordination of activities across multiple sites: IRB, HPV vaccination policy, CCLs.
  Development of materials: Google drive, email, shared protocols.
Seeking Group Input
Expansion of work: additional uses for data, related topics to address.
Potential grant funding, consultant partnerships.