## Slide 1: Lessons Learned from Implementing My Own Health Report
Catherine Rohweder, DrPH
Jennifer Leeman, DrPH, MDiv
Alexis Moore, MPH
UNC Chapel Hill and the MOHR Research Team
CPCRN Annual Meeting, Denver CO
10/3/13
This presentation was supported by Cooperative Agreement Number INSERT YOUR CENTER'S NUMBER HERE from the Centers for Disease Control and Prevention. The findings and conclusions in this presentation are those of the author(s) and do not necessarily represent the official position of the Centers for Disease Control and Prevention.

## Slide 2: Clinic Recruitment
Pre-existing relationships can make a difference at the beginning
  Quicker start-up and initial buy-in
However, relationship-building occurs throughout the study so it is possible to catch up

## Slide 3: Incorporating the MOHR Into Routine Practice
MOHR as a separate tool from the electronic health record was a barrier for some clinics
  Felt less like quality improvement and more like research
  Did not like having to ask duplicate questions (e.g. tobacco, alcohol, depression)

## Slide 4: Incorporating the MOHR Into Routine Practice
MOHR as a separate tool was not a barrier for other clinics
  Took advantage of long waiting times to engage patient in discussions about their health
  Providers liked the focus on physical activity and nutrition which are often missing from the electronic health record

## Slide 5: Data Collection Protocols
Need to monitor enrollment closely and make adjustments in eligibility criteria as necessary
Use of a proctor ensured higher quality of data and better response rates, but sacrificed real-world applicability
Contracting out the patient experience survey to the patient satisfaction survey vendor was highly successful

## Slide 6: Provider Response to the MOHR
Variability in provider receptivity towards the MOHR within and across clinics
Some providers found their mid-study report findings to be useful and motivating; others were disinterested

## Slide 7: Study Resources
Higher level of patient support requires higher level of clinic and/or research team involvement
Resources could be allocated at varying levels later in the process according to clinic capacity and patient need

## Slide 8: Publications and Planned Analyses
Methods paper in Implementation Science
Measuring reach and factors that influenced completion of the MOHR
Assessing effect of MOHR on counseling and goal setting
Describing context in which MOHR was implemented
Calculating practice implementation expenditures
Modeling effects of different implementation approaches