## Slide 1
FQHC Workgroup
Overview
Partner FQHCs, state, regional & national associations
Advance dissemination and implementation of cancer prevention and control programs
Goal – Identify factors associated with implementation of Cancer Control EBI
  To inform implementation intervention development
  To inform FQHC QI efforts
Guided by real world health policy landscape and dynamic local ecology

## Slide 2: FQHC Workgroup Discussion
Good stage to engage partners -state & regional
Year 3 goals
  Engage FQHCs/PCAs
  Focus group/Appreciative Inquiry
  Complete cross-site survey
    develop/implement/analyze
  Provide survey results to FQHCs/PCAs
  Collect information/discuss pilot studies for intervention - consider implementation tools
Year 4/5 goals
  Collaborate with FQHCs to submit proposal on implementation intervention (P01/R01)

## Slide 3: FQHC Workgroup Discussion
Cross-site survey
  Criteria
    Guided by conceptual framework
      coherent set of constructs
    Addresses changeable construct(s) for FQHCs
    Of value to the FQHCs
    Tied to implementation outcome(s)
    Available measures
    Brief

## Slide 4: FQHC Workgroup Discussion
Methods
  Framing in terms of issues important to FQHCs
  Target audience
  Engage FQHCs, PCAs, NACHC, HRSA
  Web-based
  CPCRN states

## Slide 5
UW to annotate how Capacity for Change (CFC) survey items map to CFIR domains/constructs (Oct 2011)
Engage partners (Oct 2011)
Each participating site appoints 1 Survey Designee
  Represent site on selection of constructs from UW CFC Survey to include/adapt (Oct/Nov 2011)
  Serve as point of contact for Partnership Committee work with FQHCs/PCAs/NACHC
Identify gaps based on selected CFIR constructs
  Participating sites to select domain/constructs (Oct 2011)
  Report to Survey Workgroup (Dec/Jan 2012)
    Available items/scales/measures
Year 3 Survey Activities & Timeline

## Slide 6
Select constructs/items to add to survey (Jan 2012)
IRB application (Feb 2012)
Refine survey/Pre-test survey (Feb-April 2012)
Recruitment of FQHCs (Jan-April 2012)
  Local/state/national
Implement survey (May/June 2012)
Data cleaning/Analysis (July/Aug 2012)
Report to FQHCs/PCAs/NACHC (Sept 2012)
  NACHC CHI and Expo Sept 7-12, 2012, Orlando FL
Year 3 Survey Activities & Timeline

## Slide 7: FQHC Workgroup Qualitative Inquiry Subgroup
Appreciative Inquiry at the 21st Annual Midwest Stream Farmworker Health Forum – Nov 10th 2011
Abstract for D&I conference – Nov 2011
Analysis Oct 2011-Jan 2012
Recommendations for survey- Jan 2012
Additional Focus groups on survey draft – P&I conference - Mar 2012
Presentation at D & I conference – Mar 2012
Manuscript – May 2012

## Slide 8: Focus of FQHCs Data Subcommittee
1
Examine FQHC data (locally & nationally)
2
Evaluate feasible projects and activities
3
Conduct relevant and important analyses in partnership with FQHCs
Build partnership across the country

## Slide 9: FQHC Data Subcommittee Current Activities
Monthly calls
  Discuss, share, learn, and develop new ideas
  “Share & Learn”/guest speaker portion and sub-committee business portion
Have 2 writing projects
  Editorial on FQHC-academic partnerships around data use
  GIS-based analyses of FQHC populations and service areas
Future activities include:
  Utilization of Uniform Data System (UDS) data
  More GIS application with FQHC populations and neighborhood

## Slide 10
Qualitative inquiry
yes
tbd
tbd
no
yes
yes
yes
no
yes
Emory
Texas A&M
Wash U
UCLA
CO
SC
UTH
UNC
UW
Survey
yes
tbd
yes
yes
yes
yes
yes
maybe
yes
FQHC Workgroup