## Slide 1: Collaborating with Primary Care Associations (PCAs) and Federally Qualified Health Center (FQHC) Partners to Increase Colorectal Cancer Screening Rates by Increasing Capacity to Implement and Evaluate Multi-level Interventions
Workgroup Co-Chairs:
Daniela B. Friedman, University of South Carolina
Catherine L. Rohweder, University of North Carolina
This presentation was supported by Cooperative Agreement Number U48 DP005030-01S5, U48 DP005021-01S4, U48 DP005014-01S2, U48 DP005053-01S1, U48 DP005000-01S2, U48 DP005013-01S1A3, and U48 DP005017-01S8 from the Centers for Disease Control and Prevention. The findings and conclusions in this presentation are those of the author(s) and do not necessarily represent the official position of the Centers for Disease Control and Prevention.
Notes: Project Objectives and Aims
Work Completed to Date
Work in Progress
Next Steps
Contribution/impact in D&I Science
Contribution/impact in Cancer Prevention and Control

## Slide 2: Project Objectives and Aims
Objective: To assess and strengthen existing colorectal cancer (CRC) screening initiatives at the patient, clinic, and community level
Specific Aim 1:
Identify the evidence-based interventions FQHCs are currently using to increase CRC screening rates
Specific Aim 2:
Identify the evidence-informed implementation strategies that FQHCs are currently using to put CRC screening interventions into practice
Specific Aim 5:
Develop, deliver, and evaluate implementation support tailored for multi-level CRC screening interventions at FQHCs
Specific Aim 3:
Identify the type of implementation supports that FQHCs are currently accessing and examine their experience with those supports
Specific Aim 4:
Investigate the readiness of FQHCs to implement and evaluate multi-level interventions to increase CRC screening rates

## Slide 3: Work Completed to Date
7/8 CPCRN sites are participating plus two affiliates
Bi-monthly calls have been held since November 2014
Evidence-based, multi-level CRC intervention and implementation strategies were presented at the 80 by 2018 Forum
Manuscript based on the results presented at the 80 by 2018 Forum has been submitted for publication
5 sub-committees have been formed
Sampling frame has been specified, survey instrument has been created and piloted; study procedures have been finalized; IRB has been submitted
Notes: Mention Florida (Alicia Best) and Arkansas (Michael Preston)
Manuscript has gone through CDC clearance, is going through NCI clearance, will be submitted to American Journal of Preventive Medicine
Five sub-committees include sampling, survey, IRB, qualitative, and analysis
Describe how survey was developed with clear framework and items based on the literature; categories include evidence-based interventions, implementation strategies, implementation support, and general organizational capacity
Describe latest sampling strategy and challenges of defining denominator (center versus clinic) and obtaining a sufficient sample size

## Slide 4: Next Steps
Surveys
July 1-September 31, 2016
Coordinating Center will manage survey logistics
Preliminary results of the survey will be used to inform interview instrument
Data Analysis
October 2016-March 2017
Interviews
October 1-December 31, 2016
Each data collection site will recruit and follow-up with assistance from PCA, ACS, and other partners
Curriculum for implementation and evaluation of interventions
May 2016 – March 2017
Being developed by UNC
Survey data will be analyzed Oct-Dec 2016
Interview data will be analyzed Jan-Mar 2017

## Slide 5: Contribution to D&I Science
Findings will advance the science of how to
Assess a delivery system’s use of multi-level intervention and implementation strategies
Build delivery system capacity to
  assess contributing factors across multiple levels
  select intervention strategies that target identified factors
  combine intervention strategies into multi-level interventions
  apply implementation strategies to integrate multi-level interventions into practice
(3) Evaluate the impact of multi-level implementation support
Notes: Not quite sure how to separate contributions to D&I versus contributions to cancer control and prevention since there is some overlap in these bullet points

## Slide 6: Contribution/Impact in Cancer Prevention and Control
Promote and support implementation of interventions that strategically target factors that contribute to CRC screening, diagnosis, and treatment across multiple levels
Accelerate demand for screening, recommendation for screening, and testing completion by moving from a single-intervention to a multi-level approach to CRC screening
Through our collaboration with FQHCs, improve care for vulnerable populations that experience greatest disparities in CRC morbidity and mortality