Implementing Multi-Level HPV Vaccination Interventions

Center and Investigators: University of North Carolina, Leeman is submitting

Goal

Training, TA, and tools (i.e., implementation supports) increasingly are used to promote the implementation of evidence-based strategies (EBS), yet little is known about how to optimize the design of implementation support interventions or to tailor them for EBS that target different levels (youth, parents, provider, health system).The goal of this project is to build on the work of partnering CPCRNs to develop an intervention that provides practitioners with the support they need to design, adapt, implement, evaluate, and sustain effective multi-level HPV interventions. Initial work will develop the intervention and assess its feasibility and preliminary effectiveness.

Activities

- Inventory tools currently in use or being developed by investigators across CPCRN centers to support implementation of HPV EBIs across multiple levels.

- Create an Internet-based menu of HPV implementation support tools (implementation toolkits, process and outcome measures, communication materials, education resources, etc.).

- Recruit local partners (vaccination or cervical cancer coalitions, FQHCs, public health or clinical PBRNs).

- Provide trainings and ongoing technical assistance to practitioners as they plan, adapt, implement, and evaluate multi-level interventions (via webinar or in-person).

- Evaluate the implementation support intervention

  - Outcomes: practitioner capacity (attitude and competence), implementation effectiveness (reach, fidelity to evidence-based strategies), intervention effectiveness (vaccine initiation, completion rates).

  - Process: perceptions of Implementation Support: feasibility/usefulness, cost, participation/exposure to Implementation Support (training, TA, tools).

- Refine the intervention.

- Write for external funding to test the intervention and/or compare the effectiveness of different approaches to delivery (e.g., in-person versus distance).

Work already done

The Community Guide and others have identified a range of evidence-based vaccination strategies that target change at different levels of the healthcare context (youth, parents, providers, healthcare systems). CPCRN Centers have translated these strategies into interventions and tools that practitioners might use to implement those EBS in practice.  The challenge now is to develop feasible and effective approaches to supporting practitioners in their efforts to plan and implement multilevel interventions that fit their practice contexts. The UNC team has experience disseminating implementation tools and providing interactive distance and in-person training and technical assistance. In our CPCRN grant proposal, we outlined the design and measures for a study that would compare the effectiveness of distance versus in-person approaches to providing implementation support.

Opportunities for partnership

Contribute interventions, tools, and expertise. Recruit and collect data from local partners. Write for publication. UNC will manage logistics of distance training and TA but would invite collaboration on its design and presentation. Develop a proposal for external funding.

Resources

- Personnel time to recruit partners, handle logistics, and paperwork

- Personnel time to collaborate on intervention and on collecting and analyzing study data

- Estimated $1,000 incentive to each participating community to incentivize data collectio